Holyoke Unites

Josh Mayer, Amanda Villarreal, Kyra Ellis-Moore, Anna Hagstrom

1) Project Description and Final Product(s):

Our project goal is to investigate the community and Resident Council of the Toepfert Apartment Complex (The Flats) for the purpose of determining the desires of the community and how these can be acted upon in accordance with regulations set forward by Housing and Urban Development (HUD) protocol as well as by the budget available to the Council.  We hope to use this information to help organize and empower the Resident Council to become self-sufficient in their leadership and structure and to create an annual plan and budget to represent the needs of the community while also promoting Holyoke Unites’s greater mission of education and literacy.

Goal Change: Largely the same, in terms of helping the community envision its goals and working within HUD guidelines, though we doubt we’ll be able to make a budget, annual plan, or actually secure the community room within the remaining time. Our main purpose now is secure to contact and steps for the resident council, if it is in their desire and capability, to work toward getting the community space to which they are entitled.

2) Task Distribution:

	Our aim is to work as a cohesive team throughout the project.  Initially, however, we will be dividing into two teams. Team 1 will be working on formalizing the Resident Council and helping them to determine the space and resources to which they are entitled by HUD and also require for their work.  These two will work alongside the Resident Council as they go before the Housing Authority during February to seek approval of the bylaws which will formalize their authority.  Additionally, this group will work to re-energize the Resident Council’s pre-existing committees. Once the Resident Council is formalized, the members of the first group will join the second.

Team 2 will begin work on the annual plan and budget (currently funded by the $25 allotted for each unit in the complex) and incorporate the visions for programming expressed by community members as well Holyoke Unites’s goal of achieving a 100% graduation rate.  This will help to frame the overall purpose behind these plans. Team 2 will begin work on possible budgetary needs/grant-writing procedures. Team 1 will join Team two and assist with these tasks.

All members of the group will meet on a regular basis to discuss tasks as well as with Betty Medina-Lichtenstein, director of Holyoke Unites, and will attend meetings of the Toepfert Resident Council whenever possible.

We were unable to break into 2 teams, as we did not meet some benchmarks we thought we would within the timeline in our desire to keep the Board involved in all actions and scheduling conflicts.

3) Timeline: (Annotations bolded)

February:

23rd - Both teams attend Resident Council meeting in Holyoke. Resident Council should finalize bylaws for council approval. Team 1: learns more about pre-existing committees and begins to plan on how specifically to re-energize them. Team 2: discusses annual plan ideas and budgetary needs.

(NOTE: We will decide who within our group will be on Team 1 and Team 2 once we get more details as to what each task will entail).

27th - Resident Council meets with Housing Commissioner for bylaw approval for placement into Housing Commissioner’s agenda.

Met with Betty Medina- Lichtenstein multiple times to discuss plans for meeting with the Resident Council Board and general project directions.

March:

First 2 weeks-

Team 1: Researches how to obtain space within local Community Center for Resident Council office (speaks with Headstart and Boys and Girls Club). Works on re-energizing projects.

Team 2: Continues to work with Resident Council on annual plan and budget formation.

By 2nd week: Have obtained space within local Community Center for Resident Council office. 

End of March: Team 1 should join Team 2.

March 13 - Submitted Spanish/English translation of Resident Council Bylaws to Betty and the Council.

March 15 - Met with Betty to discuss meeting with Resident Council Board and tentative plan for full resident meeting.

March 28 - Met with Resident Council Board to discuss plan of action for full resident meeting.

April:

Mid-April - Have nearly solidified an annual plan/budget with Resident Council.

End of April - Finish annual plan and budget alongside Resident Council, which will serve as a framework for them as they move into the future.

April 4 - Met with Residents of Teopfert/ Full Resident Council to discuss their vision of the use of a Community Space. Completed a list of priorities for space use (in both Spanish and English).

April 25 - (Tentative) Final meeting with Resident Council Board. Discuss resident vision and a plan of action.

May

Try to do more research into securing office space to leave the Board in a self-sustaining state by May 7.
 
Reasons for being we are where we are:

  - We were not initially able to meet with the Council at the beginning of the semester because of the bed bug problem within the building.

  - Resident council president was in Puerto Rico for a month between 	February and March, so it was difficult to plan a meeting with the Board.

  - We did not want to meet and make plans of action without coordinating with the Board.

  - Multiple times it was hard to coordinate a meeting between the majority of our team members’ busy schedules and Betty’s busy schedule.

  - Multiple meetings (with Betty and/or the Resident Council Board) were canceled due to weather, family circumstances, potential evictions, and other extenuating circumstances:.